## C500 documents
阶段 | ETA | 文档 | 难度系数 | 文档编号 | 内容 | 需求时间 | 文档作者 | 工作量（中文版本） | 工作量（英文版本） | 总计 | 参考 | 风险和问题 | Support/资源 需求（人力、工具） | 质量标准和持续改进计划
P1 （Leads） | ETA:Before May, 2022 | 公司介绍文档 |  | 无 | 现有ppt+更新数据表 |  |  | 需要更新的内容不多，五月底更新一版，PM提供相关信息。 | 英文版本暂无需求。 | 英伟达编程指南，API参考这些文档，动不动几万、十几万，我们这边刚开始不会这么多内容，是用英伟达的字数除以4计算的。有的文档，比如安装指南，内容应该大差不差，就按英伟达的字数或者除以2来计算。后续有了更多的信息再及时更新。 因为是从零开始，没有可供参考的资料和术语库，刚开始需要花很多时间去查找确认。暂时是按照中文每天3000到3500字，英文每天1000到1500字的工作量来预估。复杂的图片、表格等的处理，需要另外计算时间。 不同的文档有不同的难度系数，一般来说翻译描述类文档难度系数更高，需要的时间更多。操作类文档内容相对容易些，但研发容易把操作类文档写的乱七八糟，整理的时候也需要时间去沟通确认。另外还要预留文档不断整理更新带来的工作量。 前面几个文档内容不多，有的已经做了，直接忽略不计了。后面这些文档量大，时间暂时估算如下，如果后面有更明确的信息，收到各部门的文档，再及时统计更新： - 中文版本：共约10个月,两个人的话5个月。 - 英文版本：共约20个月一人，两个人的话10个月。这个是按照全部中文都需要翻译成英文来算。如果按照剑飞说的，英文版本会删减很多，不会全部翻译成英文，暂时除以2，那就是10个月1个人，两个人的话5个月。 | CUDA_Installation_Guide_Linux 1.2万 words CUDA_C_Programming_Guide 12.5万 words CUDA_Driver_API 9万 CUDA Profiler User Guide 4万 Compiler SDK 3.5万 CUDA_Quick_Start_Guide 4000 words NVIDIA HPC SDK Installation Guide 1600 HPC Compilers User's Guide 5万 HPC Compiler Reference Manual 5万 CUDA Compiler Driver NVCC 1.4万 编程模型：共17.5万 C++ 3500 OpenACC Getting Started Guide 1.2万 CUDA_C_Programming_Guide 13万 CUDA FORTRAN PROGRAMMING 3万 数学库：共23万 CUBLAS_Library 6万 CUFFT_Library 2.5万 CUSOLVER_Library 7.3万 CUSPARSE_Library 6.7万 CUDA Debugger 16000 |  | 对标英伟达A100：安培架构 | 数字量化风险 高风险、低风险 监督过程，不只是查结果
| ETA:Before 22Q1 | C500_通用计算加速卡_产品彩页 |  | 无 | 产品图片、概述、数据表（算力、显存/带宽、video/jpeg codec、外形规格PCIe/SCM/MCM/带宽、互联metalink/带宽、多实例GPU、功耗）、SW Stack、性能比较（AI训练/推理ResNet-50、DLRM、BERT, HPC Quantum Espresso、NAMD） |  |  | 中文版已经完成70%。 | 英文版本暂无需求，可一天完成。 |  |  |  |  | 制定并持续改进checklist 应急计划 buffer 风险 Plan B 质量目标 质量标准checklist
| ETA:Before August, 2022 | C500_通用计算加速卡_应用方案简介 |  | AB-22002-020_V1.0 | 1、HPC APP catalog 2、多卡互联（metalink）与集群计算（MCCL, MPI, Magma, OPEN_SHMEM）方案 3、MetaX Deep Learning Solution brief（maca DNN，Model zoo，AI framework containers） 4、MetaX虚拟化方案（AI and HPC） |  |  | 中文6000 中文文档两天内整理完成。 | 英文文档一周内完成。
P2 （Opportunity） | ETA:Before August, 2022 | C500_通用计算加速卡_产品简介 |  | PB-22002-020_V1.0 | 1. 概述 2. 规格 2.1 产品规格 2.2 内存规格 2.3 环境和可靠性指标 3. 散热要求 4. 过温保护 5. 支持的气流方向 6. 外形尺寸 7. 认证/机构 |  |  | 中文1500，很多是些参数信息。 中文文档一天内完成。 | 英文文档一天完成。
| ETA:Brief 22Q2/Detail 22Q3 | C500_通用计算加速卡_架构白皮书 |  | WP-22001-020_V1.0 | 1、Introduction 2、MetaX C500 GPU Overview and Key Features Summary a)C500 GPU overall architecture b)C500 GPU XCORE c)C500 GPU AP Architecture (Mixed Precision support for AI and HPC) d) HBM2e and Cache (data move path) e)Multi-Instance GPU (MIG) f)Metalink2.0 (topology and bandwidth) g)PCIe Gen 5 with SR-IOV 17 h)Video/JPEG VPU 3、SW Stack a)MACAMACA introductiion b)MACAMACA Advances for MetaX C500 GPUs 4、Conclusion Appendix A - Performance（AI and HPC） |  |  | 中文版本：是否需要中文版本再讨论。 英译中，中文版本两周内完成。 | 参考：英伟达白皮书18000 英文18000 英文版本研发写的差不多了，一周内整理完成。
| ETA:Before August, 2022 | 产品性能数据表（Performance Datasheet）：（More details vs P1） a) AI Performance b）HPC Performance |  | PD-22001-020 | 参考MLPerf: Deep Learning Performance HPC Performance - https://developer.nvidia.com/hpc-application-performance |  |  | 共两篇文档，内容可能比较多，很多表格参数信息。 中文版本：每篇一周，共两周内完成。 | 英文文档，每篇一周，共两周内完成。
P3 （Evaluation） | ETA:23Q1 | MACAMACA Toolkit Documentation: The NVIDIA CUDA Toolkit provides a comprehensive development environment for C and C++ developers building GPU-accelerated applications. |  |  | Installation Guides、 Programming Guides、 API References、 Tools: compiler、 profiler-debugger |  |  | 8.7万，共6周。 1. 安装指南：1.2 万。中文文档4天内完成。 2. 编程指南：内容很多，3万。中文文档10天内完成。 3. API参考：2.5万。中文文档八天内完成。 4. 编译器：1万。 中文版本四天内完成。 5. Profiler-debugger: 1万（PDF50多页）。中文版本四天内完成。 | 共 2个月3周完成。 1. 安装指南：1.2 万。英文文档七天内完成。 2. 编程指南：内容多，3万。英文文档 一个月内完成。 3. API参考：2.5万。 英文版本三周内完成。 4. 编译器：1万。 英文版本七天内完成。 5. Profiler-debugger: 1万（PDF50多页）。英文版本七天内完成。 | MACAMACA C++编程指南: CSPG-22001-000 Tools: mxcc Reference Guide: CSOG-22001-001 mxobjdump Reference Guide: CSOG-22002-001 Installation Guide: MACAMACA Quick Start Guide: CSOG-22003-001
| ETA:23Q1 | CUDA代码迁移指南 |  |  | Environment、Installation Guides、Steps、Demo |  |  | 暂定1.5万，中文文档一周内完成。 | 英文文档两周内完成。
| ETA:23Q1 | MetaX AI Inference User Guide Inference Library Optimized Frameworks Tools |  |  | 概述、架构、功能说明、SDK API和编程指南、示例;（ONNX-RT，Auto-Quantizer） NVIDIA TensorRT is an SDK for high-performance deep learning inference. It includes a deep learning inference optimizer and runtime that delivers low latency and high throughput for deep learning inference applications. The core of NVIDIA TensorRT is a C++ library that facilitates high-performance inference on NVIDIA GPUs. TensorRT takes a trained network, which consists of a network definition and a set of trained parameters, and produces a highly optimized runtime engine that performs inference for that network. |  |  | 暂定6万。中文文档一个月内完成。 | 英文文档两个月内完成。
| ETA:23Q1 | MetaX AI Toolkit（Training） |  |  | macaDNN，MCCL，Auto-Quantizer |  |  | 暂定6万。中文文档一个月内完成。 | 英文文档两个月内完成。 | MACAMACA PyTorch User Guide: CSOG-22005-021_V1.0 mcDNN Developer Guide: CSOG-22005-021_V1.0
| ETA:23Q1 | MetaX HPC SDK: The NVIDIA HPC SDK is a comprehensive suite of compilers, libraries, and development tools used for developing HPC applications for the NVIDIA platform. |  |  | HPC SDK Release Notes HPC SDK Install Guide Compilers (advantage to speed up HPC ) （HPC有专门的编译器吗 MACAMACA那里也有编译器？？） Programming Models (C++, Fortran, OpenMP, OpenACC...) （一两个文档） Math Libraries (BLAS, FFT, Sparse， Random，Eigen, Thrust, CUB, Solver, ...) （一两个文档） Communications Libraries (MCCL, MPI, Magma, OPEN_SHMEM) （一两个文档） Tools（profiler-debugger） |  |  | 共21万字。中文版本3个月内完成。 发布说明：内容少，忽略不计。 安装指南：1600。中文版本一天内完成，英文版本一天内完成。 编译器：2.8万。中文版本9天完成，英文版本三周内完成。 编程模型：4.5万。中文版本三周内完成，英文版本六周内完成。 数学库：共6万。中文版本一个月内完成。英文版本两个月内完成。 通信库：暂定6万。中文版本一个月内完成。英文版本两个月内完成。 工具：Profiler-debugger: 1万。（PDF50多页）中文版本四天内完成，英文版本七天内完成。 | 英文版本六个月内完成。 | mcBLAS_API_Reference: CSRD-22001-021_V1.0 mcFFT_API_Reference: CSRD-22002-021_V1.0 mcBLAS_API_Reference: CSRD-22003-021_V1.0
P4 (Bidding) | 23Q1 | 招投标技术参数与方案 |  |  | 根据投标内容确定 |  |  | 暂定3万。中文版本两周内完成。 | 英文版本一个月内完成。
P6 (Deployment) | 23Q1 | Databook(原则上仅内部使用)
| 23Q1 | Register file(原则上仅内部使用)
| 23Q1 | GPU Management and Deployment Documentation: This documentation should be of interest to cluster admins and support personnel of enterprise GPU deployments. It includes: monitoring and management tools application programming interfaces (APIs) in-field diagnostics and health monitoring cluster setup and deployment |  |  | This documentation should be of interest to cluster admins and support personnel of enterprise GPU deployments. It includes monitoring and management tools and application programming interfaces (APIs), in-field diagnostics and health monitoring, and cluster setup and deployment. |  |  | 3万。中文版本两周内完成。 | 英文版本一个月内完成。
| 23Q1 | MetaX Profiler Developer Tools Documentation | [5 empty] | 1万。中文版本四天内完成。 | 英文版本七天内完成。
| 23Q1 | MetaX Virtual GPU (vGPU) Software Documentation |  |  | NVIDIA virtual GPU (vGPU) software is a graphics virtualization platform that extends the power of NVIDIA GPU technology to virtual desktops and apps, offering improved security, productivity, and cost-efficiency. |  |  | 5万。中文版本三周内完成。 | 英文版本六周内完成。

## Deep Learning Performance
Reproducible Performance | Reproduce on your systems by following the instructions in the Measuring Training and Inferencing Performance on NVIDIA AI Platforms Reviewer’s Guide Measuring-Training-and-Inferencing-Performance-on-NVIDIA-AI-Platforms-21.09.pdf
Related Resources | Read why training to convergence is essential for enterprise AI adoption. https://developer.nvidia.com/blog/updating-ai-product-performance-from-throughput-to-time-to-solution/
Learn how Cloud Service, OEMs Raise the Bar on AI Training with NVIDIA AI in the MLPerf training. https://blogs.nvidia.com/blog/2021/12/01/mlperf-ai-cloud-service-oems/
Access containers in the NVIDIA NGC™ catalog. https://catalog.ngc.nvidia.com/collections
Learn how MLPerf Benchmarks show why AI is the future of HPC. https://blogs.nvidia.com/blog/2021/11/17/mlperf-hpc-ai/
HPC Performance | Review the latest GPU-acceleration factors of popular HPC applications. https://developer.nvidia.com/hpc-application-performance NVIDIA HPC Application Performance
Training to Convergence
PyTorch ¦ Precision: Mixed ¦ Dataset: Wikipedia 2020/01/01 ¦ Convergence criteria - refer to MLPerf requirements
MLPerf Training Performance NVIDIA A100 Performance on MLPerf 1.1 AI Benchmarks - Closed Division
Framework | Network | Dataset
MXNet | ResNet-50 v1.5 | ImageNet2012
| SSD | COCO2017
| 3D U-Net | KiTS19
PyTorch | BERT | Wikipedia 2020/01/01
| Mask R-CNN | COCO2017
| RNN-T | LibriSpeech
TensorFlow | MiniGo | Go
NVIDIA Merlin HugeCTR | DLRM | Criteo AI Lab’s Terabyte Click-Through-Rate (CTR)
NVIDIA A100 Performance on MLPerf 1.0 Training HPC Benchmarks: Strong Scaling - Closed Division
Framework | Network | Dataset
MXNet | CosmoFlow | CosmoFlow N-body cosmological simulation data with 4 cosmological parameter targets
PyTorch | DeepCAM | CAM5+TECA climate simulation with 3 target classes (atmospheric river, tropical cyclone, background)
NVIDIA A100 Performance on MLPerf 1.0 Training HPC Benchmarks: Weak Scaling - Closed Division
Framework | Network | Dataset
MXNet | CosmoFlow | CosmoFlow N-body cosmological simulation data with 4 cosmological parameter targets
PyTorch | DeepCAM | CAM5+TECA climate simulation with 3 target classes (atmospheric river, tropical cyclone, background)
Converged Training Performance of NVIDIA A100, A40, A30, A10, T4 and V100
Framework | Network | Dataset
MXNet | ResNet-50 v1.5 | ImageNet2012
PyTorch | Mask R-CNN | COCO 2014
| SSD v1.1 | COCO 2017
| Tacotron2 | LJSpeech 1.1
| WaveGlow | LJSpeech 1.1
| Jasper | LibriSpeech
| Transformer | wmt14-en-de
| FastPitch | LJSpeech 1.1
| GNMT V2 | wmt16-en-de
| NCF | MovieLens 20M
| BERT-LARGE | SQuaD v1.1
| Transformer-XL Large | WikiText-103
| Transformer-XL Base | WikiText-103
| BERT-Large Pre-Training P1 | Wikipedia+BookCorpus
| BERT-Large Pre-Training P2 | Wikipedia+BookCorpus
| BERT-Large Pre-Training E2E | Wikipedia+BookCorpus
Tensorflow | ResNet-50 v1.5 | ImageNet2012
| ResNext101 | Imagenet2012
| SE-ResNext101 | Imagenet2012
| U-Net Industrial | DAGM2007
| U-Net Medical | EM segmentation challenge
| VAE-CF | MovieLens 20M
| Wide and Deep | Kaggle Outbrain Click Prediction
| BERT-LARGE | SQuaD v1.1
| Electra Base Fine Tuning | SQuaD v1.1
| EfficientNet-B4 | ImageNet2012
| V-Net Medical | Hippocampus head and body from Medical Segmentation Decathlon
FastPitch throughput metric frames/sec refers to mel-scale spectrogram frames/sec ¦ Server with a hyphen is a pre-production server BERT-Large = BERT-Large Fine Tuning (Squadv1.1) with Sequence Length of 384 BERT-Large Pre-Training Sequence Length for Phase 1 = 128 and Phase 2 = 512 ¦ Batch Size for Phase 1 = 65,536 and Phase 2 = 32,768 EfficientNet-B4: Mixup = 0.2 ¦ Auto-Augmentation ¦ cuDNN Version = 8.0.5.39 ¦ NCCL Version = 2.7.8 Starting from 21.09-py3, ECC is enabled
Converged Training Performance of NVIDIA GPU on Cloud
Framework | Network | Dataset
PyTorch | BERT-LARGE | SQuaD v1.1
Tensorflow | BERT-LARGE | SQuaD v1.1
BERT-Large = BERT-Large Fine Tuning (Squadv1.1) with Sequence Length of 384 Starting from 21.09-py3, ECC is enabled
Converged Multi-Node Training Performance of NVIDIA GPU
Framework | Network | Dataset
PyTorch | BERT-LARGE Pre-Training P1 | SQuaD v1.1
| BERT-LARGE Pre-Training P2 | SQuaD v1.1
| BERT-LARGE Pre-Training E2E | SQuaD v1.1
BERT-Large Pre-Training Phase 1 Sequence Length = 128 BERT-Large Pre-Training Phase 2 Sequence Length = 512 Starting from 21.09-py3, ECC is enabled
Single-GPU Training
Single GPU Training Performance of NVIDIA A100, A40, A30, A10, T4 and V100
AI Inference
MLPerf Interence
Real-world inferencing demands high throughput and low latencies with maximum efficiency across use cases. An industry-leading solution lets customers quickly deploy AI models into real-world production with the highest performance from data center to edge. Related Resources Learn how NVIDIA landed top performance spots on all MLPerf Inference 1.1 tests. Read the inference whitepape（NVIDIA AI FOR GPU-ACCELERATED DEEP LEARNING INFERENCE.pdf） to explore the evolving landscape and get an overview of inference platforms. Power high-throughput, low-latency inference with NVIDIA’s complete solution stack: Achieve the most efficient inference performance with NVIDIA® TensorRT™ running on NVIDIA Tensor Core GPUs. Maximize performance and simplify the deployment of AI models with the NVIDIA Triton™ Inference Server. Pull software containers from NVIDIA NGC to race into production.
MLPerf Inference v1.1 Performance Benchmarks Offline Scenario - Closed Division
MLPerf Inference v1.1 Performance Benchmarks Server Scenario - Closed Division
MLPerf Inference v1.1 Performance Benchmarks Power Efficiency Offline Scenario - Closed Division
MLPerf Inference v1.1 Performance Benchmarks Power Efficiency Server Scenario - Closed Division
Network | Throughput | Dataset | Target Accuracy
ResNet-50 v1.5 | xxx samples/sec | ImageNet
SSD ResNet-34 |  | COCO
3D-UNet |  | BraTS 2019
RNN-T |  | LibriSpeech
BERT |  | SQuAD v1.1
MLPerf™ v1.1 Inference Closed: ResNet-50 v1.5, SSD ResNet-34, RNN-T, BERT 99% of FP32 accuracy target, 3D U-Net, DLRM 99% of FP32 accuracy target: 1.1-033, 1.1-037, 1.1-039, 1.1-042, 1.1-043, 1.1-046, 1.1-047, 1.1-048, 1.1-051. MLPerf name and logo are trademarks. See https://mlcommons.org/ for more information. BERT-Large sequence length = 384. DLRM samples refers to 270 pairs/sample average 4x1g.6gb and 7x1g.10gb is a notation used to refer to the MIG configuration. In this example, the workload is running on 4 or 7 single GPC slices, each with 6GB or 10GB of memory on a single A30 and A100 respectively. For MLPerf™ various scenario data, click here For MLPerf™ latency constraints, click here
Inference Performance of NVIDIA A100, A40, A30, A10, A2, T4 and V100
NVIDIA A100 BERT Inference Benchmarks
Inference Image Classification on CNNs with TensorRT
MLPerf Inference v1.1 Performance Benchmarks Power Efficiency Server Scenario - Closed Division
A100 Full Chip Inference Performance( A100, A40, A30, A10, A2, T4 and V100)
A100 1/7 MIG Inference Performance
A100 7 MIG Inference Performance
Network | Batch Size | Full Chip Throughput | Latency (ms) | GPU | Server | Container | Precision | Dataset | Framework | GPU Version
ResNet-50 | 1/2/8/128/223 | 11,468 images/sec | 0.7 | 1x A100 | DGX A100 | 21.09-py3 | INT8 | Synthetic | TensorRT 8.0.3 | A100 SXM-80GB
ResNet-50v1.5
ResNext101
EfficientNet-B0
BERT-BASE | [7 empty] | Sample Text
BERT-LARGE
AI Pipeline
Conversational AI NVIDIA Riva is an application framework for multimodal conversational AI services that deliver real-time performance on GPUs. Related Resources Download and get started with NVIDIA Riva.https://developer.nvidia.com/riva/getting-started